## JIRA_Sheet
Issue Type | Issue key | Issue id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Custom field (BRD complete) | Status | Resolution | Created | Updated | Due date | Custom field (Time Stamp) | Custom field (Severity) | Custom field (Severity)
Bug | LA-22605 | 50840 | LEAP Combo application - Multiple secondary application is getting created for the same combo ID. | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Rahul.Rajbhar2 | 63bc15a298bf50328c6827fe | 20 |  | Open |  | 2024-12-26 16:56 | 2024-12-26 19:11 |  |  |  | Critical
Bug | LA-22604 | 50839 | LEAP Combo application - - Primary application synced to Instadb. However the Instadb not triggered for the Secondary. | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Rahul.Rajbhar2 | 63bc15a298bf50328c6827fe | 20 |  | Open |  | 2024-12-26 16:54 | 2024-12-26 16:54 |  |  |  | Critical
Bug | LA-22599 | 50804 | Wrong format received for "product_pitched" in VYMO response for channels other than Branch Banking for HDFC ¦¦ Combo | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Mohit Agrawal | 5ff56db08332a1010ee8776c | High |  | Open |  | 2024-12-26 14:24 | 2024-12-26 16:32 |  |  |  | Blocker
Bug | LA-22585 | 50782 | Incorrect Mapping of Illustration | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-12-25 15:53 | 2024-12-25 15:53 |  |  |  | Critical
Bug | LA-22579 | 50754 | In HDFC PreFill for Offline payment method getReceipt Service req issue | Chetan Rajpurohit | 61aeee35d5986c006a894bb4 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-24 12:42 | 2024-12-26 11:05 |  |  |  | Critical
Bug | LA-22565 | 50725 | Data Missing issue | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-23 12:29 | 2024-12-23 18:40 |  |  |  | Critical
Bug | LA-22558 | 50715 | completedProgressMilestones.isDocumentSubmitted and completedProgressMilestones.isRnaSubmitted was still set to FALSE while isInstadbSyncSuccess got TRUE | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-21 20:52 | 2024-12-21 20:55 |  |  |  | Critical
Bug | LA-22557 | 50714 | Not able to select No in Health Info page. | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-12-21 15:57 | 2024-12-21 18:00 | 2024-12-21 |  |  | Critical
Bug | LA-22556 | 50713 | Axis bank Journey - RNA otp box is not showing. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-12-21 10:20 | 2024-12-21 10:20 | 2024-12-21 |  |  | Critical
Bug | LA-22553 | 50709 | Primary case payment not completed still insta sync service called for secondary app | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-20 19:11 | 2024-12-20 19:12 |  |  |  | Critical
Bug | LA-22552 | 50708 | benefitPayoutFrequencyQst (ASSURED_PAYOUT_OPTION) Store issue for NAP Plan | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-20 18:30 | 2024-12-23 12:31 |  |  |  | Critical
Bug | LA-22516 | 50662 | ABSLI Akshaya Plan - sumAssuredQst field is showing incorrect amount | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-19 14:10 | 2024-12-19 14:16 |  |  |  | Critical
Bug | LA-22510 | 50655 | HDFC Netbanking and HDFC prefill OTP SP assisted details are not getting saved in DB | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Rahul.Rajbhar2 | 63bc15a298bf50328c6827fe | 20 |  | Open |  | 2024-12-19 12:33 | 2024-12-26 11:20 |  |  |  | Critical
Bug | LA-22488 | 50629 | First name in Nominee details is not getting updated. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-12-19 10:53 | 2024-12-19 10:54 | 2024-12-19 |  |  | Major
Bug | LA-22476 | 50609 | PLAN_OPTION Store issue for AST Plan | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-18 16:30 | 2024-12-24 14:22 |  |  |  | Critical
Bug | LA-22471 | 50604 | Application is AUTO Force Coded but still it's getting opened from LEAP application | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-18 14:22 | 2024-12-18 14:22 | 2024-12-18 |  |  | Major
Bug | LA-22468 | 50601 | COMBO PLAN ISSUE - Two Secondary application was created for single primary application sharing same Combo ID | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-18 13:31 | 2024-12-26 19:11 |  |  |  | Critical
Bug | LA-22458 | 50588 | Advisor details not reflecting in ecdf milestone | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-18 12:02 | 2024-12-18 12:02 | 2024-12-18 |  |  | Critical
Bug | LA-22446 | 50536 | IDFC mobile no issue | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-12-16 18:55 | 2024-12-17 12:10 |  |  |  | Critical
Bug | LA-22417 | 50490 | Document cm_sync status was true in document collection for below cases although LEAP got fault response from CM sync service. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Ready for PreProd |  | 2024-12-16 13:03 | 2024-12-26 13:30 |  |  |  | Major
Bug | LA-22416 | 50489 | Unable to trigger link in RNA milestone | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-16 12:58 | 2024-12-26 17:17 | 2024-12-16 |  |  | Critical
Bug | LA-22411 | 50483 | AADHAR CARD [Backpage] is not passed during Hyperverge call | Aishwarya Anand | 63a3e2cb030d706ab0e2ce72 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-12-16 12:15 | 2024-12-18 14:56 |  |  |  | Critical
Bug | LA-22390 | 50439 | OTP in ecdf link is received to the USM/SSM/ASM agent instead of Advisor. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-13 18:11 | 2024-12-13 18:11 | 2024-12-13 |  |  | Minor
Bug | LA-22372 | 50414 | Unable to reupload the document in the journey after rejection from CSE | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-13 13:23 | 2024-12-13 13:23 | 2024-12-13 |  |  | Minor
Bug | LA-22367 | 50392 | Axis Bank RNA Issue - In RNA link OTP field is not available | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-13 11:06 | 2024-12-13 15:35 |  |  |  | Blocker
Bug | LA-22338 | 50312 | RNA issue - Specified key does not exist | Satish Manohar Khedekar | 62834a4fc6092d00690e4d21 | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | In UAT |  | 2024-12-11 11:51 | 2024-12-26 12:54 |  |  |  | Blocker
Bug | LA-22331 | 50291 | ASSURED_PAYOUT_OPTION field is generating value as "1" for applications which has age below 50 years. The value should have been NULL | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-10 18:29 | 2024-12-26 15:57 |  |  |  | Critical
Bug | LA-22321 | 50267 | Auto Receipting status is not reflecting in App tracker | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-12-10 13:13 | 2024-12-10 13:17 |  |  |  | Critical
Bug | LA-22318 | 50260 | (Dummy Ticket) Milestone Name - Short Description of isue | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-12-10 12:24 | 2024-12-21 20:55 |  |  |  | Critical
Bug | LA-22309 | 50240 | ecdf subbmit button not working | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-12-09 18:02 | 2024-12-10 13:20 |  |  |  | Major
Bug | LA-22308 | 50238 | "TRAN_TYP" field received NULL value due to which insta sync is getting failed | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-12-09 16:50 | 2024-12-26 14:49 |  |  |  | Critical
Bug | LA-22300 | 50203 | Sales_Without_Agent flag was set as "Yes" for DSF channel whereas it contains default value as "NO" | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-12-06 18:05 | 2024-12-09 14:06 |  |  |  | Blocker
Bug | LA-22288 | 50173 | Gender & Salutation blank | Atrik Shah | 712020:df2be560-ab46-40c9-a5e7-055c397add17 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-12-05 15:38 | 2024-12-11 11:37 |  |  |  | Critical
Bug | LA-22285 | 50170 | DOB and Name missing | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-12-05 14:18 | 2024-12-09 14:07 |  |  |  | Critical
Bug | LA-22273 | 50137 | Incorrect premium pay amount captured in customer eccd pdf. | Sarthak Singh | 712020:8bc24d23-9d3a-4cba-aba5-71002f1edb91 | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-12-04 17:48 | 2024-12-18 17:20 | 2024-12-04 |  |  | Major
Bug | LA-22263 | 50120 | Incomplete HDFC NetBanking /Pre Fill cases are insta sync | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-12-04 12:11 | 2024-12-11 14:58 |  |  |  | Critical
Bug | LA-22261 | 50118 | While instasync, the NEFT/IMPS flag was provided erroneously | Chetan Rajpurohit | 61aeee35d5986c006a894bb4 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-12-04 11:53 | 2024-12-11 15:00 |  |  |  | Major
Bug | LA-22234 | 50044 | Insurer CCD short link not working | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-12-02 14:45 | 2024-12-10 16:05 |  |  |  | Critical
Bug | LA-22231 | 50040 | ACV Doc not available in CM. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-12-02 13:20 | 2024-12-23 12:57 | 2024-12-02 |  |  | Major
Bug | LA-22230 | 50039 | No options displayed in the Non-Medical documents tile to upload the required documents.(FEE not called) | Satish Manohar Khedekar | 62834a4fc6092d00690e4d21 | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | In UAT |  | 2024-12-02 13:01 | 2024-12-26 12:54 | 2024-12-02 |  |  | Major
Bug | LA-22229 | 50038 | Unable to do cm sync LA53610884 | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-12-02 12:59 | 2024-12-12 17:10 |  |  |  | Blocker
Bug | LA-22218 | 50019 | Joint Life case issue | Atrik Shah | 712020:df2be560-ab46-40c9-a5e7-055c397add17 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-11-30 12:53 | 2024-12-05 12:08 |  |  |  | Major
Bug | LA-22216 | 50017 | Payment milestone is BLANK for applications | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-11-29 18:48 | 2024-12-06 11:28 |  |  |  | Blocker
Bug | LA-22205 | 49989 | Personal Info page is locked even if all the details are submitted | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Ready for PreProd |  | 2024-11-29 13:15 | 2024-12-17 10:29 |  |  |  | Major
Bug | LA-22173 | 49904 | Pivc link is not available on insta portal. | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Reopened |  | 2024-11-27 12:26 | 2024-12-24 13:43 | 2024-11-27 |  |  | Minor
Bug | LA-22133 | 49847 | HDFC Minor case GetPIVCDetails (instaverify) service not called | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-11-26 12:35 | 2024-11-27 16:27 |  |  |  | Critical
Bug | LA-22132 | 49846 | Payment status not getting updated at Leap from Shared Services end | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-11-26 12:15 | 2024-11-27 11:51 | 2024-11-26 |  |  | Minor
Bug | LA-22131 | 49845 | ESI Bypassed. | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-11-26 12:10 | 2024-12-18 10:59 | 2024-11-26 |  |  | Minor
Bug | LA-22128 | 49842 | Upload button is disabled for SI mandate form in the document milestone | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Cancelled |  | 2024-11-26 11:53 | 2024-12-09 12:18 | 2024-11-26 |  |  | Major
Bug | LA-22114 | 49826 | Application completed but still leap showing 75% completed | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-11-26 11:11 | 2024-11-26 14:38 |  |  |  | Critical
Bug | LA-22113 | 49825 | Application is completed but not insta synced. | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-11-26 11:09 | 2024-12-11 14:11 | 2024-11-26 |  |  | Critical
Bug | LA-22112 | 49824 | D2C case - User is getting error after providing OTP "Customer address details are not received from the bank data. Please get it updated in HDFC bank and proceed" | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-11-26 11:07 | 2024-11-28 11:31 |  |  |  | Minor
Bug | LA-22092 | 49789 | For all D2C cases of Salaried term Plan, Payment is getting failed | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-11-25 12:29 | 2024-11-26 16:42 |  |  |  | Critical
Bug | LA-22087 | 49758 | Customer CCD pdf not generated. |  |  | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Invalid |  | 2024-11-23 13:54 | 2024-12-20 17:23 | 2024-11-23 |  |  | Minor
Bug | LA-22080 | 49740 | Axis cases ASM, ZSM code are not store & same has been not passed to RWS | Aishwarya Anand | 63a3e2cb030d706ab0e2ce72 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Requirement Addition |  | 2024-11-22 16:10 | 2024-11-26 14:38 |  |  |  | Critical
Bug | LA-22076 | 49722 | Enach document not created on successfully completing the ENACH process online | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Done |  | 2024-11-22 12:36 | 2024-12-06 12:57 | 2024-11-22 |  |  | Critical
Bug | LA-22071 | 49713 | Payment method missing in Premium Renewal details object. | Aishwarya Anand | 63a3e2cb030d706ab0e2ce72 | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-11-22 11:22 | 2024-12-17 10:29 | 2024-11-22 |  |  | Critical
Bug | LA-22060 | 49683 | Address details not store | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-11-21 15:55 | 2024-11-21 16:14 |  |  |  | Critical
Bug | LA-22051 | 49667 | Application has been completed but still Payment and Documents is locked |  |  | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Under Observation |  | 2024-11-21 11:22 | 2024-12-09 12:10 |  |  |  | Blocker
Bug | LA-22044 | 49657 | RWS acknowledment value is blank in DB for Auto receipting cases. | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Open |  | 2024-11-20 14:36 | 2024-11-20 14:37 | 2024-11-20 |  |  | Critical
Bug | LA-22033 | 49646 | Axis Proposer details not fetch issue | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-11-20 12:20 | 2024-11-25 21:09 |  |  |  | Blocker
Bug | LA-22025 | 49638 | PLAN ABSLI Wealth Infinia CASES FAILED IN COVERAGE CREATION | Sachin Pasi | 62f0bce2da8620d5339412b5 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-11-19 17:47 | 2024-11-25 12:47 |  |  |  | Critical
Bug | LA-22015 | 49610 | CSB BANK LIMITED - Bank account number consists of 18 digits but user can fill only 17 digits | Abhay.Kamath | 62a991649ffc930068e181e5 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-11-18 17:10 | 2024-11-26 14:14 |  |  |  | Critical
Bug | LA-22004 | 49591 | JOURNEY PENDING STILL DROPOUT LINK SHOWS APPLICATION COMPLETED | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Done |  | 2024-11-16 15:52 | 2024-12-24 13:26 |  |  |  | Blocker
Bug | LA-22003 | 49433 | Personal info not able to complete for Retired | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-11-14 20:55 | 2024-11-25 11:28 |  |  |  | Critical
Bug | LA-22002 | 49431 | Wrong value received from Elixer for the occupation field | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Done |  | 2024-11-14 18:25 | 2024-12-05 12:31 | 2024-11-14 |  |  | Major
Bug | LA-21999 | 49402 | Advisor Code is missing and not store |  |  | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Under Observation |  | 2024-11-14 14:22 | 2024-12-09 13:53 |  |  |  | Critical
Bug | LA-21998 | 49401 | rwsHeaderFirstEntryTimestamp set even we got fault response from service | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-11-14 14:00 | 2024-11-25 11:28 |  |  |  | Critical
Bug | LA-21990 | 49364 | ABSLI Platinum Gain Plan - Policy Term issue | Sachin Pasi | 62f0bce2da8620d5339412b5 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-11-13 19:02 | 2024-12-23 10:10 |  |  |  | Critical
Bug | LA-21986 | 49355 | HDFC NetBanking ABSLI DigiShield Plan - Annual income in leap should be min 5L but no validation is provided at Select Plan Page. | Abhay.Kamath | 62a991649ffc930068e181e5 | Mithila Ajit Sawant | 712020:1cec21ff-847a-4687-959b-36c0f864605e | 20 |  | Open |  | 2024-11-13 12:42 | 2024-12-24 13:06 | 2024-11-13 |  |  | Critical
Bug | LA-21970 | 49320 | user unable to select Educational Stage in customer profile page |  |  | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Under Observation |  | 2024-11-12 11:35 | 2024-11-13 11:30 | 2024-11-12 |  |  | Blocker
Bug | LA-21963 | 49307 | Policy number generated for the application but not displayed in application tracker | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Cancelled |  | 2024-11-11 16:06 | 2024-11-13 14:51 | 2024-11-11 |  |  | Minor
Bug | LA-21962 | 49306 | Prod ¦ Axis Leads ¦ Leap stages are out of Sync [Post 12 stage we are getting 10 as stage] | Satish Manohar Khedekar | 62834a4fc6092d00690e4d21 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-11-11 16:06 | 2024-12-09 14:13 |  |  |  | Major
Bug | LA-21959 | 49289 | Case not sync to instaDB "CA_REF_A" is blank | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-11-11 13:49 | 2024-11-13 16:21 |  |  |  | Critical
Bug | LA-21945 | 49235 | App not opening in app tracker | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Cancelled |  | 2024-11-09 13:14 | 2024-11-12 10:54 |  |  |  | Blocker
Bug | LA-21944 | 49233 | USM,RSM & ZSM available in DB but not push into RWS header. | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-11-08 18:35 | 2024-12-17 12:29 |  |  |  | Critical
Bug | LA-21936 | 49219 | Not able to complete ECDF Journey | Sarthak Singh | 712020:8bc24d23-9d3a-4cba-aba5-71002f1edb91 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-11-08 13:51 | 2024-12-18 12:38 |  |  |  | Critical
Bug | LA-21933 | 49215 | County code dispplayed in UI was incorrect against the mobile no for app no LA53586226 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Cancelled |  | 2024-11-08 12:36 | 2024-12-10 20:17 | 2024-11-08 |  |  | Minor
Bug | LA-21932 | 49214 | Dummy Application Number passed in INSTADB |  |  | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Under Observation |  | 2024-11-08 12:35 | 2024-12-04 12:35 |  |  |  | Blocker
Bug | LA-21911 | 49134 | Occupation Details Missing in Ingenium for Policy Sourced Through Leap | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-11-06 14:57 | 2024-11-06 16:06 |  |  |  | Major
Bug | LA-21904 | 49121 | submittedOn field is not getting generated | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-11-06 11:30 | 2024-12-11 12:22 |  |  |  | Critical
Bug | LA-21895 | 49096 | Need reasons for delay in force coding | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-11-05 16:08 | 2024-11-06 11:05 |  |  |  | Minor
Bug | LA-21887 | 49087 | Under Age Proof tab - the Document Upload drop down is BLANK | Parth Thakkar | 712020:d8096f79-e391-4a14-a81d-4bf26b09ddfd | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Highest |  | In Dev |  | 2024-11-05 13:48 | 2024-11-26 14:58 |  |  |  | Blocker
Bug | LA-21879 | 49073 | USER UNABLE TO LOGIN LEAP | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-11-04 22:13 | 2024-11-06 11:10 |  |  |  | Critical
Bug | LA-21870 | 49059 | WIN BACK CASE, CSE PENDING STILL RWS HEADER GOT SYNCED |  |  | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Under Observation |  | 2024-11-04 17:29 | 2024-12-09 13:59 |  |  |  | Blocker
Bug | LA-21868 | 49057 | CASE IS NOT AUTO FORCE CODED | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Cancelled |  | 2024-11-04 17:18 | 2024-11-12 12:24 |  |  |  | Blocker
Bug | LA-21853 | 49034 | RWS Header sync service not called for FT,AR & Cheque cases | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Open |  | 2024-11-04 14:04 | 2024-12-06 13:55 |  |  |  | Critical
Bug | LA-21846 | 49019 | Nominee details are entered but the same is missing in front end. | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Reopened |  | 2024-11-02 13:40 | 2024-11-22 18:16 | 2024-11-02 |  |  | Critical
Bug | LA-21823 | 48983 | Prefill OTP case - For Proposer and Insurer different case, recommended plans is showing as blank | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-10-30 13:58 | 2024-11-04 13:34 |  |  |  | Blocker
Bug | LA-21821 | 48980 | Not getting E-CDF link for App No LA53569374 | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-10-30 13:31 | 2024-11-07 15:17 |  |  |  | Critical
Bug | LA-21820 | 48979 | Bank customer id was null in LEAP DB due to which customer was not able to proceed after payment page | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Cancelled |  | 2024-10-30 13:19 | 2024-12-11 11:28 | 2024-10-30 |  |  | Minor
Bug | LA-21819 | 48978 | createdby name stored in DB and that displayed in App tracker is different | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Under Observation |  | 2024-10-30 13:12 | 2024-11-25 16:46 |  |  |  | Critical
Bug | LA-21807 | 48953 | isPersonalandProfessionalSubmitted field is not getting generated even if the Journey was completed | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-10-29 12:49 | 2024-11-06 11:55 |  |  |  | Minor
Bug | LA-21804 | 48925 | "isPaymentSubmitted" key is not getting generated after Payment got completed | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-10-28 16:36 | 2024-11-07 10:12 |  |  |  | Minor
Bug | LA-21801 | 48918 | Payment Lounge payment status is not updated | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Backend Dependent |  | 2024-10-28 14:31 | 2024-12-26 16:45 |  |  |  | Critical
Bug | LA-21799 | 48915 | Platinum Gain Plan is not visible as an incorrect value is passed for field "Channel" | Abhay.Kamath | 62a991649ffc930068e181e5 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-10-28 13:30 | 2024-11-04 16:13 |  |  |  | Blocker
Bug | LA-21792 | 48896 | Force coding issue LA53539919 | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-26 10:53 | 2024-11-06 14:38 |  |  |  | Critical
Bug | LA-21764 | 48847 | Case not sync to insta db - missing NEFT Cancelled Cheque | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-24 18:26 | 2024-10-28 16:04 |  |  |  | Blocker
Bug | LA-21763 | 48844 | For HUF, user not able to select Wealth Infinia Plan | VIJENDRA KUNDEKAR | 62834ada0685de006fd05055 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-10-24 17:26 | 2024-10-31 12:34 |  |  |  | Blocker
Bug | LA-21762 | 48843 | Axis Channel Address Issue - Address was passed in Axis CRM but was not present in Leap | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-10-24 17:22 | 2024-10-24 17:22 |  |  |  | Critical
Bug | LA-21761 | 48842 | ANNUAL INCOME ISSUE LA53562757 | KIRAN BHAAVAN MEHTA | 636cf6f74bca78179baae7a0 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-10-24 17:19 | 2024-12-24 13:07 |  |  |  | Critical
Bug | LA-21758 | 48833 | Required doc's not uploaded still set completed due to this case not sync to instaDB | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-24 14:46 | 2024-12-24 11:39 |  |  |  | Critical
Bug | LA-21756 | 48831 | bank details issue | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-10-24 12:59 | 2024-12-17 12:43 |  |  |  | Critical
Bug | LA-21748 | 48795 | mandateAmt field was blank, due to which user was not able to proceed with Payment Journey |  |  | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Under Observation |  | 2024-10-23 14:20 | 2024-11-07 11:47 |  |  |  | Critical
Bug | LA-21744 | 48783 | Annual income issue For buy online cases(D2C) | Sachin Pasi | 62f0bce2da8620d5339412b5 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-23 11:45 | 2024-11-04 11:45 |  |  |  | Critical
Bug | LA-21732 | 48761 | HDFC ESI Payment module issue |  |  | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Under Observation |  | 2024-10-22 18:34 | 2024-12-10 13:32 |  |  |  | Critical
Bug | LA-21726 | 48745 | ENACH Issue - User has successfully completed ENACH still Leap shows status as "PENDING" |  |  | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Under Observation |  | 2024-10-22 16:04 | 2024-11-07 11:47 |  |  |  | Critical
Bug | LA-21716 | 48726 | RNA pending still application showing completed . | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-10-22 11:31 | 2024-10-22 11:31 |  |  |  | Critical
Bug | LA-21685 | 48649 | INCORRECT DETAILS CAPTURED IN ILLUSTRATION | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Sagar Rathod | 712020:b71b789e-4255-4b5c-8b42-352c258ab7a0 | 20 |  | Cancelled |  | 2024-10-18 16:42 | 2024-11-25 15:08 |  |  |  | Critical
Bug | LA-21684 | 48648 | unable to complete journey LAS0068149 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Open |  | 2024-10-18 16:41 | 2024-12-09 13:52 |  |  |  | Critical
Bug | LA-21679 | 48630 | Pay Term & Policy Term store 0 and passed wrong value in other lower system | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Cancelled |  | 2024-10-18 15:04 | 2024-12-09 13:51 |  |  |  | Critical
Bug | LA-21657 | 48591 | Minor insurance details data not passing in instadbDataSyncActivity | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-10-17 17:53 | 2024-11-06 15:52 |  |  |  | Blocker
Bug | LA-21631 | 48547 | USER UNABLE TO LOGIN LEAP | Rahul.Rajbhar2 | 63bc15a298bf50328c6827fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-17 15:13 | 2024-10-17 18:37 |  |  |  | Blocker
Bug | LA-21617 | 48514 | Payment mode issue | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-16 17:47 | 2024-10-22 14:39 |  |  |  | Critical
Bug | LA-21602 | 48484 | Customer ECCD Button is not visible due to which PDF is not getting generated | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-10-16 12:05 | 2024-12-24 17:05 |  |  |  | Critical
Bug | LA-21570 | 48432 | BSLI Guaranteed Milestone Plan - For Semi Annual, Quarterly and Annual Pay Mode the premium payment amount is greater than 30K | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Invalid |  | 2024-10-14 18:59 | 2024-10-15 16:09 |  |  |  | Critical
Bug | LA-21548 | 48376 | Digitally Verified documents got rejected by CSE | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Done |  | 2024-10-11 16:33 | 2024-11-04 11:44 |  |  |  | Major
Bug | LA-21547 | 48375 | Case_Client_Addr_Info.STATE issue in leap | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Under Observation |  | 2024-10-11 16:30 | 2024-10-15 17:56 |  |  |  | Critical
Bug | LA-21544 | 48368 | BSLI Wealth Aspire Plan Plan Option issue | Atrik Shah | 712020:df2be560-ab46-40c9-a5e7-055c397add17 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-11 14:18 | 2024-11-07 15:06 |  |  |  | Critical
Bug | LA-21540 | 48359 | Payment mode is annual but CIS form showing monthly | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-11 11:17 | 2024-12-11 10:30 |  |  |  | Critical
Bug | LA-21531 | 48339 | For AR cases RWS herder sync not call | Aarti Malusare | 712020:30232189-b737-4623-8f65-62effb4568c4 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-10 17:39 | 2024-10-17 15:34 |  |  |  | Critical
Bug | LA-21524 | 48323 | "missing NEFT Cancelled Cheque" | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Cancelled |  | 2024-10-10 16:17 | 2024-10-28 11:18 |  |  |  | Critical
Bug | LA-21500 | 48277 | User Unable To Complete The Journey | Atrik Shah | 712020:df2be560-ab46-40c9-a5e7-055c397add17 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-09 19:21 | 2024-10-15 15:22 |  |  |  | Critical
Bug | LA-21497 | 48259 | RWS header entry is not getting completed for applciations created | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Rakesh Yadav | 712020:6f639f67-ab41-45c1-94b4-358fda18a9d7 | 20 |  | Invalid |  | 2024-10-09 17:17 | 2024-10-10 18:00 |  |  |  | Critical
Bug | LA-21495 | 48253 | "isInstaVideoCaptured" field is not getting captured for AXIS bank Channel (CN00031) | Virendra Minanath Arekar | 712020:21cbbf5b-b88e-4027-9abb-3fd3bd7ae7fe | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-10-09 13:09 | 2024-10-10 11:13 |  |  |  | Critical
Bug | LA-21488 | 48236 | AXIS bank details are missing in ACV doc's | Atrik Shah | 712020:df2be560-ab46-40c9-a5e7-055c397add17 | Vikas Yadav | 712020:8edf1b03-9ee4-4824-8646-fa9ce6b4feeb | 20 |  | Done |  | 2024-10-08 16:33 | 2024-10-17 17:37 |  |  |  | Critical
Bug | LA-21483 | 48229 | NRI Mandate Page Issue - Even if User claims NRI account as "NO", user is asked to mention Type of Account which is a mandatory field. | MaheshGundekar | 5fe4835f642089014187b962 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-10-08 13:03 | 2024-10-10 16:14 |  |  |  | Critical
Bug | LA-21474 | 48206 | Address Page Issue - communicationAddress.country shows as "INDIA" even if the proposer/insurer is "NRI" | MaheshGundekar | 5fe4835f642089014187b962 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-10-07 18:23 | 2024-11-12 11:55 |  |  |  | Critical
Bug | LA-21471 | 48201 | IDFC Issue - Payment was done twice for same lead with 2 different application number | Sarthak Singh | 712020:8bc24d23-9d3a-4cba-aba5-71002f1edb91 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Reopened |  | 2024-10-07 17:38 | 2024-11-12 11:55 |  |  |  | Major
Bug | LA-21460 | 48180 | CM sync issue due to (px-cis-form-pdf.js) LA53529682 | Sachin Pasi | 62f0bce2da8620d5339412b5 | sushant joshi | 6315ccc3ea661fd37d4fc9a1 | 20 |  | Done |  | 2024-10-07 12:36 | 2024-10-09 15:57 |  |  |  | Critical
Bug | LA-21408 | 48086 | Advisor_Code is giving "null" value for DSF channel (C000001) |  |  | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Under Observation |  | 2024-10-03 16:03 | 2024-12-04 13:06 |  |  |  | Major
Bug | LA-21407 | 48085 | Payment Issue - Payment has been done using Lounge option but shows Pending in LEAP | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-10-03 15:33 | 2024-11-20 13:01 |  |  |  | Major
Bug | LA-21400 | 48055 | Select Plan Page and Payment page Issue - Initial Premium amount calculated at View Quote page and amount displayed at Payment page is incorrect | Sachin Pasi | 62f0bce2da8620d5339412b5 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Open |  | 2024-10-01 15:12 | 2024-10-03 17:14 |  |  |  | Blocker
Bug | LA-21350 | 47965 | isAddressConfirmed field shows value as "FALSE" even if user completes the Address section | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | High |  | Done |  | 2024-09-27 18:07 | 2024-10-08 12:47 |  |  |  | Critical
Bug | LA-21347 | 47956 | IsPaymentSubmitted field was not present in completedProgressMilestones array even if the Payment was completed | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-09-27 15:14 | 2024-09-30 13:33 |  |  |  | Minor
Bug | LA-21311 | 47888 | Received value in Incorrect format of City in â€˜Case_Client_Addr_Infoâ€™ | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-09-25 16:00 | 2024-09-27 13:35 |  |  |  | Major
Bug | LA-21309 | 47883 | Payment Page Issue - Mismatch in the initial premium for a captioned case | Aarti Malusare | 712020:30232189-b737-4623-8f65-62effb4568c4 | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Requirement Addition |  | 2024-09-25 15:19 | 2024-10-11 11:35 |  |  |  | Critical
Bug | LA-21307 | 47881 | PAN Card Invalid issue - User unable to complete the application due to PAN error | Hitesh Mishra | 712020:30766575-fa63-4e30-8411-9f52612d9cea | Umesh Gupta | 712020:f0318af4-da3e-4b6d-bd4e-8fb26be0d45a | 20 |  | Cancelled |  | 2024-09-25 15:08 | 2024-09-27 12:18 |  |  |  | Minor

## Filtered_JIRA_Sheet
Issue Type | Issue key | Summary | Assignee | Reporter | Status | Severity | Applications Affected | Created
Bug | LA-22605 | LEAP Combo application - Multiple secondary application is getting created for the same combo ID. | Hitesh Mishra | Rahul.Rajbhar2 | Open | Critical | 23 | 2024-12-26
Bug | LA-22604 | LEAP Combo application - - Primary application synced to Instadb. However the Instadb not triggered for the Secondary. | Hitesh Mishra | Rahul.Rajbhar2 | Open | Critical | 25 | 2024-12-26
Bug | LA-22599 | Wrong format received for "product_pitched" in VYMO response for channels other than Branch Banking for HDFC ¦¦ Combo | Hitesh Mishra | Mohit Agrawal | Open | Blocker | 11 | 2024-12-26
Bug | LA-22585 | Incorrect Mapping of Illustration | Virendra Minanath Arekar | sushant joshi | Open | Critical | 16 | 2024-12-25
Bug | LA-22579 | In HDFC PreFill for Offline payment method getReceipt Service req issue | Chetan Rajpurohit | Vikas Yadav | Open | Critical | 21 | 2024-12-24
Bug | LA-22565 | Data Missing issue | Hitesh Mishra | Vikas Yadav | Open | Critical | 15 | 2024-12-23
Bug | LA-22558 | completedProgressMilestones.isDocumentSubmitted and completedProgressMilestones.isRnaSubmitted was still set to FALSE while isInstadbSyncSuccess got TRUE | Virendra Minanath Arekar | Umesh Gupta | Open | Critical | 18 | 2024-12-21
Bug | LA-22557 | Not able to select No in Health Info page. | Mithila Ajit Sawant | Mithila Ajit Sawant | Open | Critical | 13 | 2024-12-21
Bug | LA-22556 | Axis bank Journey - RNA otp box is not showing. | Virendra Minanath Arekar | Mithila Ajit Sawant | Open | Critical | 17 | 2024-12-21
Bug | LA-22553 | Primary case payment not completed still insta sync service called for secondary app | Virendra Minanath Arekar | Vikas Yadav | Open | Critical | 13 | 2024-12-20
Bug | LA-22552 | benefitPayoutFrequencyQst (ASSURED_PAYOUT_OPTION) Store issue for NAP Plan | Hitesh Mishra | Vikas Yadav | Open | Critical | 21 | 2024-12-20
Bug | LA-22516 | ABSLI Akshaya Plan - sumAssuredQst field is showing incorrect amount | Virendra Minanath Arekar | Umesh Gupta | Open | Critical | 12 | 2024-12-19
Bug | LA-22510 | HDFC Netbanking and HDFC prefill OTP SP assisted details are not getting saved in DB | Hitesh Mishra | Rahul.Rajbhar2 | Open | Critical | 15 | 2024-12-19
Bug | LA-22488 | First name in Nominee details is not getting updated. | Virendra Minanath Arekar | Mithila Ajit Sawant | Open | Major | 11 | 2024-12-19
Bug | LA-22476 | PLAN_OPTION Store issue for AST Plan | Hitesh Mishra | Vikas Yadav | Open | Critical | 23 | 2024-12-18
Bug | LA-22471 | Application is AUTO Force Coded but still it's getting opened from LEAP application | Virendra Minanath Arekar | Rakesh Yadav | Open | Major | 21 | 2024-12-18
Bug | LA-22468 | COMBO PLAN ISSUE - Two Secondary application was created for single primary application sharing same Combo ID | Virendra Minanath Arekar | Umesh Gupta | Open | Critical | 19 | 2024-12-18
Bug | LA-22458 | Advisor details not reflecting in ecdf milestone | Virendra Minanath Arekar | Rakesh Yadav | Open | Critical | 22 | 2024-12-18
Bug | LA-22446 | IDFC mobile no issue | Virendra Minanath Arekar | Vikas Yadav | Open | Critical | 17 | 2024-12-16
Bug | LA-22417 | Document cm_sync status was true in document collection for below cases although LEAP got fault response from CM sync service. | Virendra Minanath Arekar | Umesh Gupta | Ready for PreProd | Major | 11 | 2024-12-16
Bug | LA-22416 | Unable to trigger link in RNA milestone | Rakesh Yadav | Rakesh Yadav | Open | Critical | 11 | 2024-12-16
Bug | LA-22411 | AADHAR CARD [Backpage] is not passed during Hyperverge call | Aishwarya Anand | Umesh Gupta | Done | Critical | 13 | 2024-12-16
Bug | LA-22390 | OTP in ecdf link is received to the USM/SSM/ASM agent instead of Advisor. | Virendra Minanath Arekar | Rakesh Yadav | Open | Minor | 17 | 2024-12-13
Bug | LA-22372 | Unable to reupload the document in the journey after rejection from CSE | Virendra Minanath Arekar | Rakesh Yadav | Open | Minor | 12 | 2024-12-13
Bug | LA-22367 | Axis Bank RNA Issue - In RNA link OTP field is not available | Virendra Minanath Arekar | Umesh Gupta | Open | Blocker | 20 | 2024-12-13
Bug | LA-22338 | RNA issue - Specified key does not exist | Satish Manohar Khedekar | Sagar Rathod | In UAT | Blocker | 10 | 2024-12-11
Bug | LA-22331 | ASSURED_PAYOUT_OPTION field is generating value as "1" for applications which has age below 50 years. The value should have been NULL | Umesh Gupta | Umesh Gupta | Open | Critical | 13 | 2024-12-10
Bug | LA-22321 | Auto Receipting status is not reflecting in App tracker | Hitesh Mishra | sushant joshi | Open | Critical | 22 | 2024-12-10
Bug | LA-22318 | (Dummy Ticket) Milestone Name - Short Description of isue | Umesh Gupta | Umesh Gupta | Invalid | Critical | 19 | 2024-12-10
Bug | LA-22309 | ecdf subbmit button not working | sushant joshi | sushant joshi | Cancelled | Major | 25 | 2024-12-09
Bug | LA-22308 | "TRAN_TYP" field received NULL value due to which insta sync is getting failed | Umesh Gupta | Umesh Gupta | Open | Critical | 25 | 2024-12-09
Bug | LA-22300 | Sales_Without_Agent flag was set as "Yes" for DSF channel whereas it contains default value as "NO" | Virendra Minanath Arekar | Umesh Gupta | Cancelled | Blocker | 13 | 2024-12-06
Bug | LA-22288 | Gender & Salutation blank | Atrik Shah | Vikas Yadav | Done | Critical | 24 | 2024-12-05
Bug | LA-22285 | DOB and Name missing | Virendra Minanath Arekar | sushant joshi | Open | Critical | 24 | 2024-12-05
Bug | LA-22273 | Incorrect premium pay amount captured in customer eccd pdf. | Sarthak Singh | Rakesh Yadav | Open | Major | 11 | 2024-12-04
Bug | LA-22263 | Incomplete HDFC NetBanking /Pre Fill cases are insta sync | Hitesh Mishra | Vikas Yadav | Done | Critical | 15 | 2024-12-04
Bug | LA-22261 | While instasync, the NEFT/IMPS flag was provided erroneously | Chetan Rajpurohit | Umesh Gupta | Done | Major | 17 | 2024-12-04
Bug | LA-22234 | Insurer CCD short link not working | Hitesh Mishra | sushant joshi | Done | Critical | 11 | 2024-12-02
Bug | LA-22231 | ACV Doc not available in CM. | Virendra Minanath Arekar | Mithila Ajit Sawant | Open | Major | 11 | 2024-12-02
Bug | LA-22230 | No options displayed in the Non-Medical documents tile to upload the required documents.(FEE not called) | Satish Manohar Khedekar | Rakesh Yadav | In UAT | Major | 17 | 2024-12-02
Bug | LA-22229 | Unable to do cm sync LA53610884 | Hitesh Mishra | sushant joshi | Cancelled | Blocker | 12 | 2024-12-02
Bug | LA-22218 | Joint Life case issue | Atrik Shah | Vikas Yadav | Done | Major | 22 | 2024-11-30
Bug | LA-22216 | Payment milestone is BLANK for applications | Hitesh Mishra | sushant joshi | Done | Blocker | 24 | 2024-11-29
Bug | LA-22205 | Personal Info page is locked even if all the details are submitted | Umesh Gupta | Umesh Gupta | Ready for PreProd | Major | 13 | 2024-11-29
Bug | LA-22173 | Pivc link is not available on insta portal. | Mithila Ajit Sawant | Mithila Ajit Sawant | Reopened | Minor | 23 | 2024-11-27
Bug | LA-22133 | HDFC Minor case GetPIVCDetails (instaverify) service not called | Hitesh Mishra | Vikas Yadav | Open | Critical | 15 | 2024-11-26
Bug | LA-22132 | Payment status not getting updated at Leap from Shared Services end | Umesh Gupta | Rakesh Yadav | Open | Minor | 21 | 2024-11-26
Bug | LA-22131 | ESI Bypassed. | Umesh Gupta | Mithila Ajit Sawant | Open | Minor | 13 | 2024-11-26
Bug | LA-22128 | Upload button is disabled for SI mandate form in the document milestone | Umesh Gupta | Rakesh Yadav | Cancelled | Major | 20 | 2024-11-26
Bug | LA-22114 | Application completed but still leap showing 75% completed | Umesh Gupta | sushant joshi | Open | Critical | 25 | 2024-11-26
Bug | LA-22113 | Application is completed but not insta synced. | Hitesh Mishra | Mithila Ajit Sawant | Open | Critical | 10 | 2024-11-26
Bug | LA-22112 | D2C case - User is getting error after providing OTP "Customer address details are not received from the bank data. Please get it updated in HDFC bank and proceed" | Umesh Gupta | Umesh Gupta | Invalid | Minor | 21 | 2024-11-26
Bug | LA-22092 | For all D2C cases of Salaried term Plan, Payment is getting failed | Hitesh Mishra | Umesh Gupta | Cancelled | Critical | 15 | 2024-11-25
Bug | LA-22087 | Customer CCD pdf not generated. |  | Rakesh Yadav | Invalid | Minor | 20 | 2024-11-23
Bug | LA-22080 | Axis cases ASM, ZSM code are not store & same has been not passed to RWS | Aishwarya Anand | Vikas Yadav | Requirement Addition | Critical | 21 | 2024-11-22
Bug | LA-22076 | Enach document not created on successfully completing the ENACH process online | Virendra Minanath Arekar | Rakesh Yadav | Done | Critical | 11 | 2024-11-22
Bug | LA-22071 | Payment method missing in Premium Renewal details object. | Aishwarya Anand | Rakesh Yadav | Open | Critical | 18 | 2024-11-22
Bug | LA-22060 | Address details not store | Hitesh Mishra | Vikas Yadav | Open | Critical | 25 | 2024-11-21
Bug | LA-22051 | Application has been completed but still Payment and Documents is locked |  | Umesh Gupta | Under Observation | Blocker | 22 | 2024-11-21
Bug | LA-22044 | RWS acknowledment value is blank in DB for Auto receipting cases. | Virendra Minanath Arekar | Rakesh Yadav | Open | Critical | 20 | 2024-11-20
Bug | LA-22033 | Axis Proposer details not fetch issue | Vikas Yadav | Vikas Yadav | Open | Blocker | 21 | 2024-11-20
Bug | LA-22025 | PLAN ABSLI Wealth Infinia CASES FAILED IN COVERAGE CREATION | Sachin Pasi | Vikas Yadav | Done | Critical | 20 | 2024-11-19
Bug | LA-22015 | CSB BANK LIMITED - Bank account number consists of 18 digits but user can fill only 17 digits | Abhay.Kamath | Umesh Gupta | Done | Critical | 19 | 2024-11-18
Bug | LA-22004 | JOURNEY PENDING STILL DROPOUT LINK SHOWS APPLICATION COMPLETED | Hitesh Mishra | Sagar Rathod | Done | Blocker | 17 | 2024-11-16
Bug | LA-22003 | Personal info not able to complete for Retired | Hitesh Mishra | sushant joshi | Done | Critical | 23 | 2024-11-14
Bug | LA-22002 | Wrong value received from Elixer for the occupation field | Rakesh Yadav | Rakesh Yadav | Done | Major | 18 | 2024-11-14
Bug | LA-21999 | Advisor Code is missing and not store |  | Vikas Yadav | Under Observation | Critical | 21 | 2024-11-14
Bug | LA-21998 | rwsHeaderFirstEntryTimestamp set even we got fault response from service | Hitesh Mishra | Vikas Yadav | Done | Critical | 14 | 2024-11-14
Bug | LA-21990 | ABSLI Platinum Gain Plan - Policy Term issue | Sachin Pasi | Vikas Yadav | Done | Critical | 25 | 2024-11-13
Bug | LA-21986 | HDFC NetBanking ABSLI DigiShield Plan - Annual income in leap should be min 5L but no validation is provided at Select Plan Page. | Abhay.Kamath | Mithila Ajit Sawant | Open | Critical | 10 | 2024-11-13
Bug | LA-21970 | user unable to select Educational Stage in customer profile page |  | Rakesh Yadav | Under Observation | Blocker | 16 | 2024-11-12
Bug | LA-21963 | Policy number generated for the application but not displayed in application tracker | Hitesh Mishra | Rakesh Yadav | Cancelled | Minor | 16 | 2024-11-11
Bug | LA-21962 | Prod ¦ Axis Leads ¦ Leap stages are out of Sync [Post 12 stage we are getting 10 as stage] | Satish Manohar Khedekar | Umesh Gupta | Open | Major | 12 | 2024-11-11
Bug | LA-21959 | Case not sync to instaDB "CA_REF_A" is blank | Hitesh Mishra | Vikas Yadav | Done | Critical | 14 | 2024-11-11
Bug | LA-21945 | App not opening in app tracker | Virendra Minanath Arekar | Sagar Rathod | Cancelled | Blocker | 10 | 2024-11-09
Bug | LA-21944 | USM,RSM & ZSM available in DB but not push into RWS header. | sushant joshi | sushant joshi | Open | Critical | 10 | 2024-11-08
Bug | LA-21936 | Not able to complete ECDF Journey | Sarthak Singh | Vikas Yadav | Open | Critical | 12 | 2024-11-08
Bug | LA-21933 | County code dispplayed in UI was incorrect against the mobile no for app no LA53586226 | Umesh Gupta | Rakesh Yadav | Cancelled | Minor | 12 | 2024-11-08
Bug | LA-21932 | Dummy Application Number passed in INSTADB |  | Sagar Rathod | Under Observation | Blocker | 24 | 2024-11-08
Bug | LA-21911 | Occupation Details Missing in Ingenium for Policy Sourced Through Leap | Hitesh Mishra | Umesh Gupta | Cancelled | Major | 15 | 2024-11-06
Bug | LA-21904 | submittedOn field is not getting generated | Umesh Gupta | Umesh Gupta | Done | Critical | 19 | 2024-11-06
Bug | LA-21895 | Need reasons for delay in force coding | Virendra Minanath Arekar | sushant joshi | Cancelled | Minor | 11 | 2024-11-05
Bug | LA-21887 | Under Age Proof tab - the Document Upload drop down is BLANK | Parth Thakkar | Umesh Gupta | In Dev | Blocker | 19 | 2024-11-05
Bug | LA-21879 | USER UNABLE TO LOGIN LEAP | Virendra Minanath Arekar | sushant joshi | Cancelled | Critical | 12 | 2024-11-04
Bug | LA-21870 | WIN BACK CASE, CSE PENDING STILL RWS HEADER GOT SYNCED |  | Sagar Rathod | Under Observation | Blocker | 20 | 2024-11-04
Bug | LA-21868 | CASE IS NOT AUTO FORCE CODED | Sagar Rathod | Sagar Rathod | Cancelled | Blocker | 10 | 2024-11-04
Bug | LA-21853 | RWS Header sync service not called for FT,AR & Cheque cases | Virendra Minanath Arekar | Vikas Yadav | Open | Critical | 15 | 2024-11-04
Bug | LA-21846 | Nominee details are entered but the same is missing in front end. | Hitesh Mishra | Rakesh Yadav | Reopened | Critical | 25 | 2024-11-02
Bug | LA-21823 | Prefill OTP case - For Proposer and Insurer different case, recommended plans is showing as blank | Hitesh Mishra | Umesh Gupta | Invalid | Blocker | 14 | 2024-10-30
Bug | LA-21821 | Not getting E-CDF link for App No LA53569374 | Hitesh Mishra | Umesh Gupta | Invalid | Critical | 13 | 2024-10-30
Bug | LA-21820 | Bank customer id was null in LEAP DB due to which customer was not able to proceed after payment page | Virendra Minanath Arekar | Rakesh Yadav | Cancelled | Minor | 17 | 2024-10-30
Bug | LA-21819 | createdby name stored in DB and that displayed in App tracker is different | Umesh Gupta | Umesh Gupta | Under Observation | Critical | 21 | 2024-10-30
Bug | LA-21807 | isPersonalandProfessionalSubmitted field is not getting generated even if the Journey was completed | Hitesh Mishra | Umesh Gupta | Invalid | Minor | 20 | 2024-10-29
Bug | LA-21804 | "isPaymentSubmitted" key is not getting generated after Payment got completed | Virendra Minanath Arekar | Umesh Gupta | Cancelled | Minor | 21 | 2024-10-28
Bug | LA-21801 | Payment Lounge payment status is not updated | Vikas Yadav | Vikas Yadav | Backend Dependent | Critical | 23 | 2024-10-28
Bug | LA-21799 | Platinum Gain Plan is not visible as an incorrect value is passed for field "Channel" | Abhay.Kamath | sushant joshi | Open | Blocker | 16 | 2024-10-28
Bug | LA-21792 | Force coding issue LA53539919 | Virendra Minanath Arekar | sushant joshi | Done | Critical | 13 | 2024-10-26
Bug | LA-21764 | Case not sync to insta db - missing NEFT Cancelled Cheque | Virendra Minanath Arekar | Vikas Yadav | Done | Blocker | 14 | 2024-10-24
Bug | LA-21763 | For HUF, user not able to select Wealth Infinia Plan | VIJENDRA KUNDEKAR | Umesh Gupta | Done | Blocker | 23 | 2024-10-24
Bug | LA-21762 | Axis Channel Address Issue - Address was passed in Axis CRM but was not present in Leap | Hitesh Mishra | Umesh Gupta | Open | Critical | 23 | 2024-10-24
Bug | LA-21761 | ANNUAL INCOME ISSUE LA53562757 | KIRAN BHAAVAN MEHTA | sushant joshi | Cancelled | Critical | 12 | 2024-10-24
Bug | LA-21758 | Required doc's not uploaded still set completed due to this case not sync to instaDB | Hitesh Mishra | Vikas Yadav | Done | Critical | 25 | 2024-10-24
Bug | LA-21756 | bank details issue | Virendra Minanath Arekar | sushant joshi | Open | Critical | 14 | 2024-10-24
Bug | LA-21748 | mandateAmt field was blank, due to which user was not able to proceed with Payment Journey |  | Umesh Gupta | Under Observation | Critical | 11 | 2024-10-23
Bug | LA-21744 | Annual income issue For buy online cases(D2C) | Sachin Pasi | sushant joshi | Done | Critical | 13 | 2024-10-23
Bug | LA-21732 | HDFC ESI Payment module issue |  | Vikas Yadav | Under Observation | Critical | 18 | 2024-10-22
Bug | LA-21726 | ENACH Issue - User has successfully completed ENACH still Leap shows status as "PENDING" |  | Umesh Gupta | Under Observation | Critical | 10 | 2024-10-22
Bug | LA-21716 | RNA pending still application showing completed . | Virendra Minanath Arekar | sushant joshi | Open | Critical | 23 | 2024-10-22
Bug | LA-21685 | INCORRECT DETAILS CAPTURED IN ILLUSTRATION | Virendra Minanath Arekar | Sagar Rathod | Cancelled | Critical | 23 | 2024-10-18
Bug | LA-21684 | unable to complete journey LAS0068149 | sushant joshi | sushant joshi | Open | Critical | 24 | 2024-10-18
Bug | LA-21679 | Pay Term & Policy Term store 0 and passed wrong value in other lower system | Virendra Minanath Arekar | Vikas Yadav | Cancelled | Critical | 18 | 2024-10-18
Bug | LA-21657 | Minor insurance details data not passing in instadbDataSyncActivity | Umesh Gupta | Umesh Gupta | Cancelled | Blocker | 22 | 2024-10-17
Bug | LA-21631 | USER UNABLE TO LOGIN LEAP | Rahul.Rajbhar2 | sushant joshi | Done | Blocker | 25 | 2024-10-17
Bug | LA-21617 | Payment mode issue | Hitesh Mishra | Vikas Yadav | Done | Critical | 23 | 2024-10-16
Bug | LA-21602 | Customer ECCD Button is not visible due to which PDF is not getting generated | Virendra Minanath Arekar | Umesh Gupta | Done | Critical | 13 | 2024-10-16
Bug | LA-21570 | BSLI Guaranteed Milestone Plan - For Semi Annual, Quarterly and Annual Pay Mode the premium payment amount is greater than 30K | Hitesh Mishra | Umesh Gupta | Invalid | Critical | 20 | 2024-10-14
Bug | LA-21548 | Digitally Verified documents got rejected by CSE | Hitesh Mishra | Umesh Gupta | Done | Major | 13 | 2024-10-11
Bug | LA-21547 | Case_Client_Addr_Info.STATE issue in leap | sushant joshi | sushant joshi | Under Observation | Critical | 19 | 2024-10-11
Bug | LA-21544 | BSLI Wealth Aspire Plan Plan Option issue | Atrik Shah | Vikas Yadav | Done | Critical | 17 | 2024-10-11
Bug | LA-21540 | Payment mode is annual but CIS form showing monthly | sushant joshi | sushant joshi | Done | Critical | 23 | 2024-10-11
Bug | LA-21531 | For AR cases RWS herder sync not call | Aarti Malusare | Vikas Yadav | Done | Critical | 21 | 2024-10-10
Bug | LA-21524 | "missing NEFT Cancelled Cheque" | Virendra Minanath Arekar | sushant joshi | Cancelled | Critical | 25 | 2024-10-10
Bug | LA-21500 | User Unable To Complete The Journey | Atrik Shah | sushant joshi | Done | Critical | 23 | 2024-10-09
Bug | LA-21497 | RWS header entry is not getting completed for applciations created | Virendra Minanath Arekar | Rakesh Yadav | Invalid | Critical | 25 | 2024-10-09
Bug | LA-21495 | "isInstaVideoCaptured" field is not getting captured for AXIS bank Channel (CN00031) | Virendra Minanath Arekar | Umesh Gupta | Cancelled | Critical | 10 | 2024-10-09
Bug | LA-21488 | AXIS bank details are missing in ACV doc's | Atrik Shah | Vikas Yadav | Done | Critical | 19 | 2024-10-08
Bug | LA-21483 | NRI Mandate Page Issue - Even if User claims NRI account as "NO", user is asked to mention Type of Account which is a mandatory field. | MaheshGundekar | Umesh Gupta | Open | Critical | 13 | 2024-10-08
Bug | LA-21474 | Address Page Issue - communicationAddress.country shows as "INDIA" even if the proposer/insurer is "NRI" | MaheshGundekar | Umesh Gupta | Open | Critical | 10 | 2024-10-07
Bug | LA-21471 | IDFC Issue - Payment was done twice for same lead with 2 different application number | Sarthak Singh | Umesh Gupta | Reopened | Major | 12 | 2024-10-07
Bug | LA-21460 | CM sync issue due to (px-cis-form-pdf.js) LA53529682 | Sachin Pasi | sushant joshi | Done | Critical | 13 | 2024-10-07
Bug | LA-21408 | Advisor_Code is giving "null" value for DSF channel (C000001) |  | Umesh Gupta | Under Observation | Major | 18 | 2024-10-03
Bug | LA-21407 | Payment Issue - Payment has been done using Lounge option but shows Pending in LEAP | Umesh Gupta | Umesh Gupta | Cancelled | Major | 17 | 2024-10-03
Bug | LA-21400 | Select Plan Page and Payment page Issue - Initial Premium amount calculated at View Quote page and amount displayed at Payment page is incorrect | Sachin Pasi | Umesh Gupta | Open | Blocker | 18 | 2024-10-01
Bug | LA-21350 | isAddressConfirmed field shows value as "FALSE" even if user completes the Address section | Hitesh Mishra | Umesh Gupta | Done | Critical | 23 | 2024-09-27
Bug | LA-21347 | IsPaymentSubmitted field was not present in completedProgressMilestones array even if the Payment was completed | Umesh Gupta | Umesh Gupta | Cancelled | Minor | 25 | 2024-09-27
Bug | LA-21311 | Received value in Incorrect format of City in â€˜Case_Client_Addr_Infoâ€™ | Umesh Gupta | Umesh Gupta | Cancelled | Major | 10 | 2024-09-25
Bug | LA-21309 | Payment Page Issue - Mismatch in the initial premium for a captioned case | Aarti Malusare | Umesh Gupta | Requirement Addition | Critical | 22 | 2024-09-25
Bug | LA-21307 | PAN Card Invalid issue - User unable to complete the application due to PAN error | Hitesh Mishra | Umesh Gupta | Cancelled | Minor | 16 | 2024-09-25

## Priority Tasks
Issue Type | Issue key | Summary | Assignee | Reporter | Priority Number | Status
Bug | LA-22605 | LEAP Combo application - Multiple secondary application is getting created for the same combo ID. | Hitesh Mishra | Rahul.Rajbhar2 | 1 | Open
Bug | LA-22604 | LEAP Combo application - - Primary application synced to Instadb. However the Instadb not triggered for the Secondary. | Hitesh Mishra | Rahul.Rajbhar2 | 2 | In Uat
Bug | LA-22599 | Wrong format received for "product_pitched" in VYMO response for channels other than Branch Banking for HDFC ¦¦ Combo | Hitesh Mishra | Mohit Agrawal | 3 | In Preprod
Bug | LA-22585 | Incorrect Mapping of Illustration | Virendra Minanath Arekar | sushant joshi | 4 | Done
Bug | LA-22579 | In HDFC PreFill for Offline payment method getReceipt Service req issue | Virendra Minanath Arekar | Vikas Yadav | 5 | Done
Bug | LA-22565 | Data Missing issue | Hitesh Mishra | Vikas Yadav | 6 | In Uat
Bug | LA-22558 | completedProgressMilestones.isDocumentSubmitted and completedProgressMilestones.isRnaSubmitted was still set to FALSE while isInstadbSyncSuccess got TRUE | Virendra Minanath Arekar | Umesh Gupta | 7 | Open
Bug | LA-22557 | Not able to select No in Health Info page. | Virendra Minanath Arekar | Mithila Ajit Sawant | 8 | Open
Bug | LA-22273 | Incorrect premium pay amount captured in customer eccd pdf. | Sarthak Singh | Rakesh Yadav | 9 | Open
Bug | LA-21936 | Not able to complete ECDF Journey | Sarthak Singh | Vikas Yadav | 10 | Open
Bug | LA-21887 | Under Age Proof tab - the Document Upload drop down is BLANK | Parth Thakkar | Umesh Gupta | 11 | In Dev
Bug | LA-21483 | NRI Mandate Page Issue - Even if User claims NRI account as "NO", user is asked to mention Type of Account which is a mandatory field. | MaheshGundekar | Umesh Gupta | 13 | Open
Bug | LA-21474 | Address Page Issue - communicationAddress.country shows as "INDIA" even if the proposer/insurer is "NRI" | MaheshGundekar | Umesh Gupta | 14 | Open
Bug | LA-21471 | IDFC Issue - Payment was done twice for same lead with 2 different application number | Sarthak Singh | Umesh Gupta | 15 | Reopened
Bug | LA-22071 | Payment method missing in Premium Renewal details object. | Aishwarya Anand | Rakesh Yadav | 16 | Open
Bug | LA-21400 | Select Plan Page and Payment page Issue - Initial Premium amount calculated at View Quote page and amount displayed at Payment page is incorrect | Sachin Pasi | Umesh Gupta | 17 | Open
Bug | LA-22033 | Axis Proposer details not fetch issue | Vikas Yadav | Vikas Yadav | 18 | Open
Bug | LA-21801 | Payment Lounge payment status is not updated | Vikas Yadav | Vikas Yadav | 19 | Backend Dependent
Bug | LA-21631 | USER UNABLE TO LOGIN LEAP | Rahul.Rajbhar2 | sushant joshi | 20 | Done